## Slide 1
Information Systems Weekly Update
Week ending 05 September 2025

## Slide 2: Summary
Departmental Summary (Key highlights for achievements - impactful)
Completed Projects New ones - old to be Under highlights slide

## Slide 3: Matters arising 1. Artificial Intelligence (AI) Initiatives
Matters arising | Use cases under development or pilot | Partnerships or platforms under consideration | AI readiness in terms of data infrastructure and skills | Previous Week achievements | Current week achievements
Artificial Intelligence (AI) Initiatives | AI based Synchronized Security | Sophos through IDSS |  |  | 
 | AI based hosted contact centre | 3CX |  |  | 
 | Zstack AI based cloud platform | Zstack | One staff member certified | One staff member certified | 

## Slide 4
Project Title | Scope | Start date | Finish date | Previous Week achievements | Current week achievements
Internal servers Upgrade | Optimization of corporate server environment | 1 Jan 2025 | 31 Dec 2025 | Internet link established for LEAP VMs | Prepared hardware for Exchange DR, including RAID configuration, networking setup, and iDRAC management configuration. Installed Windows Server for the Exchange Server Disaster Recovery (DR) environment. Quote for High Density server from Shadong received
Cloud Data Centre Upgrade | Increase computing and storage resources | 1 Jan 2025 | 31 Dec 2025 | Negotiated a price review for Fibre Switches and an upgrade of storage capacity to 300TB | Direct purchase request for 154k storage and 2 fibre switches in circulation
Projects under implementation/planning/development

## Slide 5
Project Title | Scope | Start date | Finish date | Previous Week achievements | Current week achievements
Network Upgrade | Optimize LAN network | 1 Jan 2025 | 31 Dec 2025 |  | Ordered 10 access points (APs) to address wireless coverage dark spots; 20% configured and tested.
Contact Centre as a Service | Subscribed cloud based contact centre | 1 Jan 2025 | 31 Dec 2025 | DP document completed for call center. | NDA document for flex Contact Centre approved by legal department
NAC Expansion | Deploy NAC nationwide Deploy Windows based or Sophos synchronized security |  | Q1-Q4 |  | Completed PacketFence NAC test for wired devices.
Projects under implementation/planning/development

## Slide 6: Cloud Data Centre Updates
Huawei FusionSphere (Old Cloud) |  |  |  |  |  |  |  |  |  | 
Usable capacity |  |  | Used Capacity |  |  | Planned Expansion |  |  | Customers | 
Storage (TB) | RAM (TB) | CPU Cores | Storage (TB) | RAM (TB) | CPU Cores | Storage (TB) | RAM (TB) | CPU Cores | Weekly Installations | Total Active
3.70 | 1.59848 | 517 | 140.36 | 4.04399 | 985 | 0 | 0 | 0 | 0 | 19
Cloudstack (New Cloud) |  |  |  |  |  |  |  |  |  | 
Usable capacity |  |  | Used Capacity |  |  | Planned Expansion |  |  | Customers | 
Storage (TB) | RAM (TB) | CPU Cores | Storage (TB) | RAM (TB) | CPU Cores | Storage (TB) | RAM (TB) | CPU Cores | Weekly Installations | Total Active
0.00 | 3.116 | 1 681.36 | 61.665 | 2.2848 | 1482 | 250 | 0 | 0 | 1 | 10
Prospective clients requirements |  |  |  | 
Name of Client | Cloud Requirements |  |  | Projected Monthly Revenue
 | Storage (TB) | RAM (TB) | CPU Cores | USD
14 X Prospective Clients | 113.9 | 1,136 | 312 | 12,767.37

## Slide 7: Information Systems Infrastructure Support
No. | Description | Progress Update 29/08/2025 | Progress Update 04/09/2025
1 | Network Support | Showground hardware and wireless infrastructure setup complete Installed 4 All in One PCs and an access point at Showgrounds LEAP internet VLAN successfully installed Call Centre renovation documents signed | Hatfied LAN fault cleared Call centre renovations completed Tidied and secured cabling in the server room
2 | Server Support | Successfully synced AD servers with the NTP server OS updates change request approved for Q3 | OS updates for 16 servers completed Provisioned 2 VMs for Telone Center for learning
3 | Systems Support | Installed 3 VPNs for internal staff | Installed 3 VPNs for internal staff
4 | System Uptime | Cloud Data center uptime 100% Server Uptime 100% Network Uptime 100% | Cloud Data center uptime 100% Server Uptime 100% Network Uptime 100%
5 | Hosted Services | Change request for Xgen server hardware repairs in circulation | 
6 | Cloud Datacentre | Held a meeting with LK cellular regarding their infrastructure as a service server requirements Deployed Oasis digital Health on Dell cloud | Civil registry IPsec site to site vpn issue resolved Created a interconnection network between Telone VPN link and Liquid Internet link for Standard Association of Zimbabwe virtual servers to access their internet Uploaded Leap Billing Production license
7 | Risk issues |  |